## Sheet1
Date | Completed / Log | Completed By | Hours Spent | Learned/Practiced | To Continue
2017-05-27 | Initial mockup of Site. Textbox with Submission functionality. Basic Navigation Bar at top of page. Initial push to GIT. | Chris Peterkin | 2 | Jquery. GIT pushing. Manipulating the DOM with JS. CSS stylzing and element hierarchy. HTML Elements.
2017-05-28 | Added "bold," "italic," and "underline" buttons. Do not function properly yet. Researched File Uploading in Jquery. | Chris Peterkin | 2 | Manipulating text in textarea to be bold, italic, or underlined. Options for Jquery file upload. AJAX seems like the best option, it updates files on to the server, but without having to render the page again. Called a dynamic process - manipulates the DOM. There are also plugins for File Uploading that are available. Created a fork in GITHub. | Make Bold, Italic, and Underline functional.
2017-05-28 | Changed color scheme for readability. Added sidebar via html+CSS. Changed hyperlinks to buttons via html+css | Shekhar Chalasani | 2 | Classes in CSS. Using <div> to separate content. Color Scheme.
2017-05-29 | Added href functionality to sidebar links. Included addition of two new html files: the profile page, and friends page. | Chris Peterkin | 1 | File navigation. | Populating the three html files differently. Home Page should have a feed. My page should have textbox and upload options. My friends should have specific friends feed.
To Do